## Defect Tracking Log
DEFECT TRACKING LOG
Project Name
Program Manager
Project Manager
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 10.01.2025 | Tarik Ganić | 1. Open Google Chrome web browser 2. Search for "www.nix.ba" 3. Do not enter anything into the search bar "Pretraga..." 4. Click on the search button 5. User is shown random number of selling items (20) EXPECTED RESULT: The following sequence of actions should result a warning by the website saying that a user has to give an input before searching SCREENSHOT https://drive.google.com/file/d/1LJbRhD_-fV1IoPfBDs6NnPPflazdyofb/view?usp=sharing | [6 empty] | New |  |  |  |  | New
2 | 10.01.2025 | Tarik Ganić | 1. Open Google Chrome web browser 2. Search for "www.nix.ba" 3. Select any of recommended categories 4. On the left side in drop-down menu "Lokacija" type any number (exp. 40) 5. For any number drop-down menu gives a different location EXPECTED RESULT: The result for typing any kind of number should not be a location such as: Srednjobosanski kanton (for the number 40), but a message saying No results or something similar. SCREENSHOT https://drive.google.com/file/d/1IsiclbEe-Z-MriRTJjNqs9RNDTteBTjH/view?usp=sharing | [6 empty] | New |  |  |  |  | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 10.01.2025 | Tarik Ganić | 1. Open Google Chrome web browser 2. Search for "www.nix.ba" 3. Select any of recommended categories 4. On the left side, while typing the range of prices for articles write in column "Od" 3 and in column "Do" 0 5. Press button "Osvjezi rezultate" 6. Page loads 20 articles that do not represent the requested values EXPECTED RESULT: Page should respond with a warning saying that the values of prices between 3 and 0 are invalid and should not present any articles. SCREENSHOT https://drive.google.com/file/d/1Qkit4ivYvWWD12c460l7tkt_VtRjAUwO/view?usp=sharing | [6 empty] | New |  |  |  |  | In Progress | Medium | Initiating | Concept
4 | 10.01.2025 | Tarik Ganić | 1. Open Google Chrome web browser 2. Search for "www.nix.ba" 3. Pressing the logo in the navbar multiple times, and scrolling down to content, results in calls to the server requesting page reload and its content for each spam-click user makes. Inspecting this in the browser’s developer tools (Network tab), I noticed that each click queues a new page load request. This likely happens because the event listeners for the logo click are stacking up instead of being properly managed. Each time the logo is clicked, a new event handler or request might be added without cleaning up previous instances. This behavior can lead to significant performance issues, especially if a user interacts with the logo frequently. EXPECTED RESULT: Page should detect spam clicks and deny additional requests for reload. SCREENSHOT https://drive.google.com/file/d/15Vd-t4jFlgVeh4km0ZXDFU1_JtXycHgD/view?usp=sharing | [6 empty] | New |  |  |  |  | Completed | Low | Planning | Requirements
5 | 10.01.2025 | Tarik Ganić | 1. Open Google Chrome web browser 2. Search for "www.nix.ba" 3. Clicking on category "Tehnologija" that has over 281 articles, without selecting any of the filters, results in showing only 20 articles. There is no pagination. There is not a way to successfully search/reach all the articles. EXPECTED RESULT: If no filters are selected, it should show the exact number of articles it says it has. SCREENSHOT https://drive.google.com/file/d/1Uy8yk5I7q9ns1BzxInggZZ4iFMLxPD7Z/view?usp=sharing | [6 empty] | New | [6 empty] | Executing/Controlling | Design
6 | [16 empty] | Closing | Development
7 | [17 empty] | Testing
8 | [17 empty] | Documentation and Training
9 | [17 empty] | Deployment
10 | [17 empty] | Post-Deployment
11
12
13
14
15
16
17
18
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).